## October-23
Date	Project Name	Assign	Task
06/10/23	UttarPradesh	Trupti Mam	Unserved Villages Tool.(Create report for Unservedvillages and add Viewon map button but its not working)
07/10/23	UttarPradesh	Trupti Mam	Unserved Villages Tool.(Viewon map function is working now and create popup for unserved villages)
08/10/23	Holiday
09/10/23	Leave
10/10/23	Uttarakhand	Imran Bhai	Uttarakhand (Make College report page in Uttarahand)
11/10/23	UttarPradesh	Trupti Mam	Unserved Villages Tool.(create popup for unserved villages and highlight roads layer on lat long.)
12/10/23	UttarPradesh	Trupti Mam	Unserved Villages Tool.(Display Village name in popup and pass token in function for viewonmap)
13/10/23	UttarPradesh	Trupti Mam	Check Unserved villages tool and dpr tool in live url.Unserved villages tool is working but in dpr tool ,layer and report is not working.so try to get all layers and reports in this tool.
14/10/23	Holiday
15/10/23	Holiday
16/10/23	Leave
17/10/23	UttarPradesh(Chakbandi)	Priyanka Mam	Check All forms in Chakbandi and find errors while save the form.and save one form Ch41.
18/10/23	UttarPradesh(Chakbandi)	Priyanka Mam	Save another forms in chakbandi like Ch45(create popup while save and update the form) and Adharvarshkhatoni.
19/10/23	UttarPradesh(Chakbandi)	Priyanka Mam	Save another forms in chakbandi like Ch23 and Ch21 and Ch11(create popup while save the form).
20/10/23	UttarPradesh(Chakbandi)	Priyanka Mam	Check All forms in Live url and its all working but ch23 is not working.change table and create validations.and finally its work.
21/10/23	UttarPradesh(Chakbandi)	Priyanka Mam	Check Ch-7-b form and change some query and data in table and save the form.
22/10/23	Holiday
23/10/23	Leave
24/10/23	Holiday
25/10/23	UttarPradesh(Chakbandi)	Priyanka Mam	Read Khatoni report Document and try to understand it from mam.and change report shreniwise.
26/10/23	UttarPradesh(Chakbandi)	Priyanka Mam	In khatoni report total and filter is not working.Total and all columns are in format.i was trying but filter is not done.
27/10/23	UttarPradesh(Chakbandi)	Priyanka Mam	I was trying to filter all datatables but still its not working.
28/10/23	Holiday
29/10/23	Holiday
30/10/23	UttarPradesh(Chakbandi)	Priyanka Mam	In khatoni report filter is done.and its working in Live Url also.
31/10/23	Holiday
01/11/23	UttarPradesh	Trupti Mam	In Unserved village tool,change table from india_roads to up_allroad and get report and layers from this table.and its working.
02/11/23	UttarPradesh	Trupti Mam	I will try to create Hybrid security in main login page.
03/11/23	UttarPradesh	Trupti Mam	Hybrid encryption is working in main login page.

## December-23
Date	Project Name	Assign	Task
01/12/23	UttarPradesh	Trupti mam	Navigation tool in UP District tool(pending)
02/12/23	UttarPradesh	Trupti mam	Navigation tool in UP District tool(completed)
03/12/23	Holiday(Niti Aayog)		Create Education form in Niti Ayog and save Form in different models.
04/12/23	Niti Ayog	Trupti mam	Create Education form in same Model and generate Report for education form & integrate it in Rakeshbhai Pc.
05/12/23	Niti Ayog	Trupti mam	Make Single Page For All Departments.Cant fetch values in state and all.(pending)
06/12/23	Niti Ayog	Trupti mam	Make Single Page For All Departments.(completed)
07/12/23	Niti Ayog	Trupti mam	In dynamic report,make all tables for all departments.
08/12/23	Niti Ayog	Trupti mam	Integrate All Departments in Rakeshbhai Pc and save all the form.Health,Nutrition,Social is still not working.(pending)
09/12/23	Niti Ayog	Trupti mam	Integrate All Departments in Rakeshbhai Pc and save all the form.(completed)
10/12/23	Holiday
11/12/23	Niti Ayog	Trupti mam	Create Report for Area developemnt in map3.and try to Edit & delete records in report.
12/12/23	Niti Ayog	Trupti mam	Fetch data from table in form when select on village dynamically in Area Development Form.
13/12/23	Niti Ayog	Trupti mam	Navigation Block in Niti District Portal.
14/12/23	UttarPradesh	Trupti mam	Hybrid Encryption in Pahunch(UttarPradesh_sec).(Pending)
15/12/23	UttarPradesh	Trupti mam	Hybrid Encryption in Pahunch(UttarPradesh_sec).(Pending)
16/12/23	Holiday	Trupti mam
17/12/23	UttarPradesh & Niti Ayog	Trupti mam	Hybrid Encryption in Pahunch(UttarPradesh_sec).(Completed) And in Niti Aayog make village level in area development and fetch data on map point.
18/12/23	Niti Ayog	Trupti mam	Submit form of Water and Sanitation in village level & check report.Show again all forms health,education & nutrition.
19/12/23	Niti Ayog	Trupti mam	Cql filter on map with navigation also.
20/12/23	Niti Ayog	Trupti mam	Add Layers in nutrition with cql.
21/12/23	Niti Ayog	Trupti mam	Make Village level and asset level and all layers in map3 page also.Try to Edit on point in map.
22/12/23	Niti Ayog	Trupti mam	Edit in Health And Nutrition on point in map in Area Development.
23/12/23	Holiday
24/12/23	Holiday
25/12/23	Holiday
26/12/23	Leave
27/12/23	Leave
28/12/23	Niti Ayog	Trupti mam	Edit in Education Area Development.
29/12/23	Niti Ayog	Trupti mam	Save geometry of Education Department(schoolname) in Assetlevel.
30/12/23	Niti Ayog	Trupti mam	Create Area Development in Map_block page & display layer also.(In School_india,layer not shown)
31/12/23	Holiday

## January-24
Date	Project Name	Assign	Task
01/01/24	Niti Ayog	Trupti mam	Create Area Development in Map_block page & display layer also.(In School_india,layer working) & save geometry of anganvadi code in nutrition.
02/01/24	Niti Ayog	Trupti mam	Save geometry of healthgid for health & all Save & edit working with proper geometry.
03/01/24	Niti Ayog	Trupti mam	Design In All 8 forms in Niti (vertical).
04/01/24	Niti Ayog	Trupti mam	Change All code in navigation_block.js & navigation.js for displaying layer bothside(viceversa)
05/01/24	Niti Ayog	Trupti mam	Change All code in navigation_district.js for displaying layer bothside(viceversa)
06/01/24	Niti Ayog	Trupti mam	Check Concentration Zone & Edit Education with table div(with design) & clear method for layers.
07/01/24	Holiday
08/01/24	Leave
09/01/24	Niti Ayog	Trupti mam	Set state in navigation when logging with Ranchi district.Set anganvadi no in icds table in both save & edit page & print msg in every save method.
10/01/24	Niti Ayog	Trupti mam	Hybrid Encryption in Niti Aayog Login page.(Pending)
11/01/24	Niti Ayog	Trupti mam	Hybrid Encryption in Niti Aayog Login page.(Complete)
12/01/24	Niti Ayog	Trupti mam	Integrate Hybrid encryption in rakeshbhai pc.but it cant send for live.
13/01/24	Holiday
14/01/24	Holiday
15/01/24	UttarPradesh	Trupti mam	PlanningTool in UP.(create lat,lon and open form)
16/01/24	UttarPradesh	Trupti mam	create Plannig Tool form.(pending)
17/01/24	UttarPradesh	Trupti mam	create Planning Tool form and save pdf after save the form.
18/01/24	UttarPradesh	Trupti mam	Do some changes in draw linestring and in form as per requirements.
19/01/24	UttarPradesh	Trupti mam	try to save satelite view image after draw linestring.(pending)
20/01/24	Leave(Half)
21/01/24	Holiday
22/01/24	UttarPradesh	Trupti mam	try to save satelite view image after draw linestring.(pending)
23/01/24	UttarPradesh	Trupti mam	try to save satelite view image after draw linestring.(complete)
24/01/24	UttarPradesh	Trupti mam	save Pdf with satelite view image and also with table and styles.
25/01/24	UttarPradesh,Niti Ayog	Trupti mam	save images in folder at server side.
26/01/24	Holiday
27/01/24	Holiday
28/01/24	Holiday
29/01/24	UttarPradesh,Niti Ayog	Trupti mam	Generate QR code from unique srno in Pdf.(cant save Qr code images).Check All form in Niti Ayog in Live(not working)
30/01/24	Leave(Full)
31/01/24	Niti Ayog	Trupti mam	Check All form in Niti Ayog in Live.update some code and now save is working(in education,not working)

## February-24
Date	Project Name	Assign	Task
01/02/24	Niti Ayog	Trupti mam	Save and Edit All forms.And also change in all navigations.And fetch some data with client side tables.(Education is not working)
02/02/24	Niti Ayog	Trupti mam	Check All form in Niti Ayog in Live.make some changes.Education is working.
03/02/24	UttarPradesh	Trupti mam	Create Qrcode and also save in mobile after scan it.(Pending)
04/02/24	Holiday
05/02/24	UttarPradesh,Nit Ayog	Trupti mam	Integrate Qrcode code and send war to check in live url.Save Water form in niti with indicator code and attribute code and remove extra columns.
06/02/24	UttarPradesh	Trupti mam	remove layers and legend from dynamic buffer layer in up.(layer removed but legend not)
07/02/24	UttarPradesh	Trupti mam	remove legend for specific layer from dynamic buffer layer in up.(working)
08/02/24	UttarPradesh	Trupti mam	Create some changes in pdf & in qrcode as per client req.
09/02/24	UttarPradesh	Trupti mam	Try to Set radius for Latitutude & Longitude on map in PlanningTool.(Not Working)
10/02/24	Holiday
11/02/24	Holiday
12/02/24	UttarPradesh	Trupti mam	Download Pdf in Irrigation Tool on Identifycontent.(Working)
13/02/24	UttarPradesh	Trupti mam	Create Pdf for PlanningTool in Html side.remove from controller side.(Not Working)
14/02/24	UttarPradesh	Trupti mam	Create Pdf for PlanningTool in Html side.(Working)
15/02/24	UttarPradesh	Trupti mam	Set radius for Latitutude & Longitude on map in PlanningTool.(Not Working)
16/02/24	Niti Ayog	Trupti mam	Set radius for Latitutude & Longitude on map in PlanningTool.(Working).Means it only make point or linestring on map with some nearest radius.
17/02/24	Niti Ayog	Trupti mam	Add Questions in filter dashboard.
18/02/24	Holiday
19/02/24	Leave
20/02/24	UttarPradesh	Trupti mam	Set radius for Latitutude & Longitude on map in PlanningTool.(Working)
21/02/24	Niti Ayog	Trupti mam	Changes in Niti Dashboard(Add Some Questions in As Question & set layers & legend)
22/02/24	Niti Ayog	Trupti mam	Change some design in Dashboard & Create Highcharts(bar & donut) in Niti Dashboard and changes in report also.
23/02/24	Niti Ayog	Trupti mam	Make All Question with proper layer & styles in Niti Dashboard & remove legend from it.
24/02/24	Holiday
25/02/24	Holiday
26/02/24	Niti Ayog	Trupti mam	Make Asc & Desc order in highchart(barchart) in niti dashboard.set one tap connection layer with style in range.Change in theme chart also.
27/02/24	Niti Ayog	Trupti mam	Create Donut chart with Percentage (also with tap_water_connection).And also make click event on donut chart for updating barchart.check all habitation & village count.
28/02/24	Niti Ayog	Trupti mam	Create donutchart from barchart click event & also generate report onclick event of barchart.
29/02/24	Niti Ayog	Trupti mam	Create barchart from donutchart click event & also generate report onclick event of barchart.special for tap_water_connection percentage wise generate report.

## March-24
Date	Project Name	Assign	Task
01/03/24	Niti Ayog	Trupti mam	Create Dynamic Gap Analyzer tool in NitiIndia.(school,health,icds)
02/03/24	Niti Ayog	Trupti mam	Integrate Dynamic Gap tool & layers also working.Remove alert & debugger in Project.
03/03/24	Holiday
04/03/24	Niti Ayog	Trupti mam	Make 7 Pilot District(With Four Groups) in Pm Gatishakti Layers.Set All Layers in Asc Order.
05/03/24	Niti Ayog	Trupti mam	Ministry layers not showing on map(solved).Set Highlight on state when click on barchart for perticular state in Niti Dashboard.
06/03/24	Niti Ayog,UttarPradesh	Trupti mam	Check map_district & map_block is not working perfectly in NitiIndia.(code mismatch).Fetch data on edit in tubewell assets.
07/03/24	Niti Ayog	Trupti mam	Check Areadevelopment tool proper working or not in stagging url.also check dyanmic gap analyzer tool in Nitiindia.(Both proper working)
08/03/24	Holiday
09/03/24	Holiday
10/03/24	Holiday
11/03/24	Pmgatishakti(JJM)	Trupti mam	Create user for Jalshakti and Check api of GetVillageWiseInformation.
12/03/24	Pmgatishakti(JJM)	Trupti mam	Create new table for insert data from GetVillageWiseInformation api.
13/03/24	Pmgatishakti(JJM)	Trupti mam	Create views from jjm_households table but in village 95k record not matched.so check mismatching code.
14/03/24	Pmgatishakti(JJM)	Trupti mam	Update data and trigger api for every 15 days.try to pass dynamic token.(but token api is not valid).
15/03/24	Niti Ayog	Trupti mam	Show Legend on legend hover button & also add satelite view button in dashboard.
16/03/24	Niti Ayog	Trupti mam	Check & create district login in Niti for same map3 page(Pending).Check api of jjm_households & it working on static token.
17/03/24	Holiday
18/03/24	Niti Ayog	Trupti mam	Save username,role & status in village level form for perticular login.
19/03/24	Niti Ayog	Trupti mam	Make Areadevtool Dashboard in Niti for District user with approve & rejection.(Working)
20/03/24	Leave(Full)
21/03/24	Niti Ayog,UttarPradesh	Trupti mam	Integrate Areadevtool Dashboard with Approve & Rejection of data.Try to set tooltip on map in niti dashboard(not working).Create max points with static linestring in planningtool in up.
22/03/24	UttarPradesh	Trupti mam	Create max points in planningtool but validation is not proper working for all points.(Pending)
23/03/24	Holiday
24/03/24	Holiday
25/03/24	Holiday
26/03/24	UttarPradesh	Trupti mam	Create max points in planningtool but validation(distanceradius) is not proper working for all points.(Pending)
27/03/24	Niti Ayog,UttarPradesh	Trupti mam	Validation in planningtool is proper working for all points using linestring.but for one point it’s not working.Check Niti Ayog Area dev tool & all layers in live with username Ashvini_Block.
28/03/24	Niti Ayog,UttarPradesh	Trupti mam	Check Indicator tool in Niti Ayog.Also validate for one point in planningtool.Condition for all distances are pending.
29/03/24	Holiday
30/03/24	UttarPradesh,Pmgatishakti (JJM)	Trupti mam	Condition for all distances are complete in planning tool.Integrate JJM Api in Tribal War with username(Ashvini_JJM) and try to run it.(Working)
31/03/24	Holiday

## April-24
Date	Project Name	Assign	Task
01/04/24	Tribal	Trupti mam	Create username for district level and Try to clip district level in Tribal.(Pending)
02/04/24	Tribal	Trupti mam	Set clip layer in district level in tribal and also in navigation tool but district code is mismatch with layer tables.
03/04/24	NitiIndia	Trupti mam	Create Asc & Dsc order barchart in state indicator chart in nitiindia.and also set different colors in all bars.
04/04/24	Tribal(CSC),Pmgatishakti	Trupti mam	Set Registration for csc_state & distict.save data from jalshakti api into jjm_habitationlevel(16,88,216) data.
05/04/24	Tribal(CSC)	Trupti mam	Create form for CSC household.
06/04/24	Tribal(CSC)	Trupti mam	Make Login credentials for CSC.Create Registration page for csc with different model & repo(csuser_csc).
07/04/24	Holiday
08/04/24	Tribal(CSC)	Trupti mam	Create Two different login credentials in tribal.(Tribal & CSC).set role in all securityconfig,otp method,captchaauthentication and also admin method.(Working)
09/04/24	Tribal(CSC)	Trupti mam	Integrate login creadentials for both in Tribal but bypass url in login is not working.change some criteria for state & district login in csc reports.
10/04/24	Holiday
11/04/24	Holiday
12/04/24	Leave(Full)
13/04/24	Holiday
14/04/24	Holiday
15/04/24	Tribal(CSC),NitiIndia	Trupti mam	bypass url in login is working successfully.add different colors in two charts state & blockwise in NitiIndia.
16/04/24	Tribal(CSC)	Trupti mam	Create Edit Form for CSC.create model & repo for csc insert mob data & fetcha all data in form.
17/04/24	Holiday
18/04/24	Assam Urban	Trupti mam	Save water supply,drainage,sewege all 12 forms in Assam.
19/04/24	Tribal(CSC)	Trupti mam	Update all data of CSC in edit function successfully.Design Csc Household Form.Integrate edit functionality in tribal war.(Working)
20/04/24	NitiIndia	Trupti mam	convert dashboard into different languages using bhashini.(show doc of bhashini app).(Not working)
21/04/24	Holiday
22/04/24	NitiIndia	Trupti mam	convert dashboard into different languages using bhashini.create method for this.(Not working)
23/04/24	Leave(Full)
24/04/24	Leave(Half)
25/04/24	Leave(Full)
26/04/24	Leave(Full)
27/04/24	Holiday
28/04/24	Holiday
29/04/24	Tribal(Napix)	Trupti mam	NapixApi code match with niti ayog table boundries.CSC Module not proper working in live solve all errors.
30/04/24	Tribal(Napix)	Trupti mam	Create table of Napix State Data and also Napix District data.Add MOPR Data in this table also.

## May-24
Date	Project Name	Assign	Task
01/05/24	Tribal(Napix)	Trupti mam	Create Napix_Village_Data using psql tool(Not Working)
02/05/24	Tribal(Napix)	Trupti mam	Create Napix_Village_Data using psql tool(Working).and match all data with district code.
03/05/24	Leave(Full)
04/05/24	Tribal(Dashboard 2.0)	Trupti mam	Make Dashboard For Tribal 2.0 (Pending).
05/05/24	Holiday
06/05/24	Tribal(Dashboard 2.0)	Trupti mam	Make Dashboard For Tribal 2.0 (Complete with design).
07/05/24	Holiday
08/05/24	Tribal(FRA)	Trupti mam	Create Forest Land Form-A with design in Tribal FRA Module.
09/05/24	Tribal(FRA)	Trupti mam	Create Forest Land Form-B and Form-C with design in Tribal FRA Module.
10/05/24	Holiday
11/05/24	Holiday
12/05/24	Holiday
13/05/24	Tribal(Dashboard 2.0,Napix)	Trupti mam	Add Count in dashboard as per grants count.add all queries for count and percentage in dashboard.some data mismatched.Create table of napix subdistrictdata from json files.
14/05/24	Tribal(Dashboard 2.0)	Trupti mam	Create Bank Dashboard for Tribal Dashboard(2.0).Make Header,Footer and section(only design with static count) for this.
15/05/24	Tribal(Dashboard 2.0)	Trupti mam	Make Map,Barchart(with dynamic count) and report in Bank Dashboard.
16/05/24	Tribal(Dashboard 2.0)	Trupti mam	Make dynamic report and also change report on barchart click function also create highlight on state on map in Bank Dashboard.
17/05/24	Tribal(Dashboard 2.0)	Trupti mam	Set All Design for Bank Dashboard and also create Report Again using pagelength code.(for fetch fast data in datatable)
18/05/24	Tribal(Dashboard 2.0)	Trupti mam	Make Health Center Dashboard in this and also set all Get Method into Post.(in 4 pages)And also change some code in report for search facility.
19/05/24	Holiday
20/05/24	Tribal(Dashboard 2.0)	Trupti mam	Create Electricity and Transportation Dashboard(specially bus,auto,van count code)for this.and also set it’s values in report.
21/05/24	MORD,FRA	Trupti mam	Make PWD Tool in MORD.Also Design IFR FRA Form in FRA.
22/05/24	FRA,Tribal(Dashboard 2.0)	Trupti mam	Delete All session attributes in dashboard count and show all with different method and simply with model attributes.Create FRA Report Page with completely Design For FRA.
23/05/24	Tribal(Dashboard 2.0)	Trupti mam	Try to make percentage count dynamic in main two dashboards and only create one method(pc gone).
24/05/24	Tribal(Dashboard 2.0)	Trupti mam	Try to create All method again in my Admincontroller from 16/05 backup.because all data is gone in my controller because of pc issue.
25/05/24	Holiday
26/05/24	Holiday
27/05/24	Tribal(Dashboard 2.0)	Trupti mam	Create All DropDown filter state,district,block and grampanchayat and bind there data from tables in Healthcenter dashboard.(Tribal VC)
28/05/24	Leave(Full)
29/05/24	Tribal(Dashboard 2.0)	Trupti mam	Now Filter Count from change event of state,district,block and gp.and also change barchart on change event also.
30/05/24	Tribal(Dashboard 2.0)	Trupti mam	Filter Report from state,district,block and gp and also howereffect on change event and clear dropdown for smoothly work.
31/05/24	Tribal(Dashboard 2.0 and PWD in MORD)	Trupti mam	Now i am going to create All dropdownlist with checkboxes.in state, its done.but cant append data in district dropdownlist.Try to create another query for Pwd tool.(not working)

## June-24
Date	Project Name	Assign	Task
01/06/24	Tribal(State Ministry sanctioned)	Trupti mam	Create State wise Ministry sanctioned dashboard with design and also show Total in footer of table.
02/06/24	Holiday
03/06/24	Tribal(State Ministry sanctioned)	Trupti mam	Make Customized csv and excel to show extra header and Total also when download it.Edit Functionality also done.
04/06/24	Tribal(State Ministry sanctioned)	Trupti mam	Create Two pages Ministry sanctioned dashboard & Statewise data in only one page using Tab(With Design).it’s proper working with downloading buttons.
05/06/24	Tribal(State Ministry sanctioned)	Trupti mam	Integrate Tab Page of Ministry sanctioned dashboard.Solve query of fast report mobile app in Tribal(Himanshi di).Get Dropdownlist with checkboxes.but multiple not working.
06/06/24	Tribal(State Ministry sanctioned & Tribal Dashboard 2.0)	Trupti mam	Set Edit functionality for perticular username only in Ministry sanctioned dashboard and also create excel and csv format again.Try to check checkboxes in tribal dashboard(not working)
07/06/24	Tribal(Tribal Dashboard 2.0)	Trupti mam	Fetch District from multiple selection of states and also get Chart & Report also for multiple selection states.
08/06/24	Holiday
09/06/24	Holiday
10/06/24
11/06/24
12/06/24
13/06/24
14/06/24
15/06/24
16/06/24	Holiday
17/06/24	Holiday
18/06/24
19/06/24
20/06/24
21/06/24
22/06/24	Holiday
23/06/24	Holiday
24/06/24
25/06/24
26/06/24
27/06/24
28/06/24
29/06/24
30/06/24	Holiday